# SKILLYME X SECRETSTARTUPS COMMUNITY STRUCTURE AND WORKFLOW

THE FULL STRUCTURE OUTLINE

PRE -SESSION

Here is a detailed, presentable workflow for your Pre-Program Info Session.

OBJECTIVE:To accelerate young tech professionals from learning to market through mentorship,skilled training and real world project experience.

### Pre-Program Info Session: The Official Kick-Off

Objective: To officially welcome all participants, present the full vision and value of the program, communicate all logistical details, and (most importantly) facilitate the crucial first step of team formation.

#### Session Overview

- Duration: 90 Minutes (Recommended)

- Format: A live, mandatory virtual event (e.g., on Zoom or Google Meet). It must be recorded for any participant who absolutely cannot attend.

- Audience: All accepted participants for the program.

#### Detailed Agenda & Workflow

This structure is designed to build excitement, deliver critical information, and move participants directly into action.

Part 1: Welcome & The Big Picture (10 Minutes)

- Topic: "Welcome: Why You're Here"

- Content:

  - A high-energy welcome from the program organizers.

  - The Vision: Briefly explain the "why" behind the program. This isn't just a series of workshops; it's a "career-building-in-a-box" experience.

  - The Goal: Frame the end-goal for the participants (e.g., "By the end of this program, you will not only have new skills but a real-world project, a professional portfolio, and direct access to recruiters and founders.").

Part 2: The 5-Stage Program Journey (25 Minutes)

- Topic: "Your Path from Learner to Professional"

- Content: This is the core "education" piece. Visually walk them through the entire program, showing how each stage builds on the last.

  - Phase 1: Soft Skills Foundation: Explain the 3-week, 5-module structure and how skills like storytelling and collaboration will be used in the hackathon.

  - Phase 2: Technical Deep-Dive: Detail the 1-week, 4-track (SE, Cloud, Data, ML) format. Emphasize that this is not "school" but a deep-dive into "real-world challenges" taught by 10+ mentors.

  - Phase 3: The Hackathon: Introduce this as the "main event" where they will apply everything from Phases 1 & 2 to build a real, cross-functional project.

  - Stage 4: The Recruiter Stage: Show them the "what's next." They will learn exactly how to get hired, using their new project and skills as proof.

  - Stage 5: The Founder Stage: Present the "alternative path"—how to think like an entrepreneur and turn their hackathon project into a potential startup.

Part 3: Logistics & Rules of Engagement (15 Minutes)

- Topic: "How It All Works: Platforms, Schedule, & Code of Conduct"

- Content:

  - Communication Hub: Introduce the WhatsApp Community as the single source of truth for all announcements, networking, and team-building.

  - Platforms: Explain what other tools will be used (e.g., "All live sessions will be on Zoom," "All code must be on GitHub").

  - Schedule: Provide a high-level overview of the weekly time commitment for each phase.

  - Code of Conduct: Briefly cover the non-negotiable rules of professionalism, respect, active participation, and collaboration.

Part 4: The First Mission: Team Formation (30 Minutes)

- Topic: "Action: Building Your 4-Stack Team"

- Content: This is the most critical action item of the session.

  - The Golden Rule: Reiterate that all project teams must be cross-functional, with at least one member from each of the 4 tech tracks (SE, Cloud, Data, ML).

  - The Process:

    - Introduce the Channels: Explain that the WhatsApp community is already divided into 4 channels (e.g., #se-track, #cloud-track, #data-track, #ml-track).

    - The "Pitch Template": Give them a simple template to post in the channels to find teammates (e.g., "Hi, I'm [Name], an [ML Engineer]. I'm passionate about [Interest, e.g., FinTech]. I'm looking for SE, Cloud, and Data teammates to build something amazing!").

  - Live Networking (If using Zoom):

    - "We will now open 4 breakout rooms, one for each tech track."

    - "Please join your specific track's room for the next 20 minutes to meet your peers and start forming groups."

    - This is the most effective way to get the ball rolling immediately.

Part 5: Open Q&A & Wrap-Up (10 Minutes)

- Topic: "What Did We Miss?"

- Content:

  - Answer any live questions from the chat.

  - Final Call to Action: Reiterate the immediate next steps:

    - Join the WhatsApp community (paste the link).

    - Start networking in your track's channel/breakout room.

    - Find your team and register it by [DEADLINE].

  - Thank them for their time and share the excitement for the program's start.

Here is a refined, presentable workflow for Phase 1, structured to show the logical progression and modular format.

### Phase 1: The Soft Skills Foundation

Objective: To equip participants with the essential soft skills required for the Phase 3 hackathon.

#### Program Overview

- Total Duration: 3 Weeks

- Format: 5 sequential, 3-day modules.

- Resources: 2-5 dedicated mentors.

#### The 3-Day Module Workflow

Each of the 5 topics will follow this consistent 3-day structure:

- Day 1: Instructional Talk

  - A mentor or expert leads a session (e.g., workshop, lecture) to introduce the core concepts of the module's topic.

- Day 2 & 3: Group-Based Task

  - Participants break into their assigned groups.

  - They receive a practical challenge or project related to the Day 1 topic.

  - The groups work collaboratively to apply the new skill, with mentors available to guide and support them.

#### Program Workflow: The 5 Modules

This workflow shows the logical progression from identifying a problem to branding the solution, building skills incrementally each week.

#### Week 1: Problem & Solution Framing

- Module 1: Problem Definition

  - Focus: Based on the topic "Identifying the problems at hand."

  - Goal: Teach participants how to move beyond surface-level symptoms to find a specific, well-defined root problem.

  - Task (Day 2-3): Groups will be given a broad scenario (e.g., "poor student engagement") and must deliver a clear, concise "Problem Statement" document.

- Module 2: Solution Design & Ideation

  - Focus: Based on the topic "Creating solutions for the problems."

  - Goal: Teach participants how to brainstorm, evaluate, and select a viable solution.

  - Task (Day 2-3): Using their "Problem Statement" from Module 1, groups will develop and present a "Solution Proposal" (e.g., a lean canvas or a feature list).

#### Week 2: Collaboration & Communication

- Module 3: Team Collaboration & Communication

  - Focus: As stated in the topic.

  - Goal: Equip teams with frameworks for agile work, constructive feedback, and conflict resolution.

  - Task (Day 2-3): Groups will be given a complex task that requires clear delegation and project management, simulating a "sprint" from the upcoming hackathon.

- Module 4: Storytelling & Pitching

  - Focus: Based on the topic "Storytelling."

  - Goal: Teach participants how to structure a compelling narrative to sell their idea to judges, users, or stakeholders.

  - Task (Day 2-3): Groups will take their "Solution Proposal" from Module 2 and build a 5-minute "pitch" deck and script, practicing its delivery.

#### Week 3: Branding & Presentation

- Module 5: Personal & Team Branding

  - Focus: Based on the topic "Personal branding."

  - Goal: Show participants how to professionally market their skills, their personal brand, and their project's identity.

  - Task (Day 2-3): Groups will create a simple "Brand Kit" for their project (name, value proposition, etc.). Individually, participants will update their professional profiles (e.g., LinkedIn) to reflect the projects and skills from this phase.

### Phase 2: Technical Preparation & Real-World Challenges

Objective: To bridge the gap between academic theory and real-world application by having participants "deep-dive" into how their specific tech stack (e.g., SE, Cloud, Data, ML) contributes to solving major, cross-functional project challenges.

#### Program Overview

- Duration: 1 Week (4 Days, Monday - Thursday)

- Format: A 4-day intensive, with each day dedicated to one "major, real-world problem" faced by technical teams.

- Resources: 10+ professional mentors, with 2-3 new mentors featured each day.

- Structure: Each day is split into two parts: a shared "All-Hands Panel" (the "Why") and track-specific "Breakout Workshops" (the "How").

#### The 4 Technical Tracks (The Breakouts)

Participants will be in one of the following four tracks for all afternoon sessions:

- Software Engineering (Frontend, Backend)

- Cloud & DevOps (Cloud Engineering - AWS/Azure/GCP, DevOps, SRE)

- Data Science & Analytics (Data Analysis, BI, Data Engineering)

- Machine Learning & AI (ML Engineering)

#### The Daily Workflow (Mon-Thu)

(we need to work on how the sessions will be structured daily/daily timetable)

PHASE 3 :HACKATHON(AI for Accessibility: Building Smart Solutions for the Student Mismatch.,Innovating student life through AI Solutions)

### 1. Hackathon Theme: The "Industry Sector" Model***********

Since the mentor talks are process-oriented (how to build) and not problem-oriented (what to build), the hackathon must provide the what.  We must provide a theme around which they can build the project or a specific problem statement that they will focus on building the solution for it.

Recommendation: A Themed Hackathon focused on 1-2 Industry Sectors.

The hackathon should not be open ended to avoid that broadness which will be hard thinking through the problem each team will be trying to solve.

- How it Works: At the kick-off, we will announce the theme. For example: "The Future of FinTech" or "Innovating for HealthTech."

- The Task: Teams must identify a problem within that sector and build a solution prototype.(it should be something that works then it can be extended later,an MVP)

### 2. Team Structure

- Team Size: This will depend on the number of individuals we bring onboard then we can form a team of 8 people so that it can be atleast 2 people in each disciplinary.

- Mandatory Composition: Each team must be interdisciplinary.

  - Software Engineering

  - Cloud & DevOps

  - Data Science & Analytics

  - Machine Learning & AI

### 3.Duration of hackathon

The hackathon will be done in a span of (x) days but am projecting a maximum of one week.

### 4.Judgement of the hackathon

Our prizes must reward the goals of the program.

Grand Prize (1 Team): The best overall project, combining technical execution, problem-solution fit, and a polished presentation.

Phase 1 Award: The "Best Collaboration" Prize

- Awarded to the team that (as observed by mentors and judges) demonstrated the best teamwork, communication, and project management—directly rewarding the soft skills.

Phase 2 Award: The "Best Technical Execution" Prize

- Awarded to the team with the most robust, well-architected, and technically impressive prototype, demonstrating they overcame the challenges discussed in Phase 2.

Best-in-Stack Awards (4 Awards)

- Best Use of Software Engineering: (e.g., best UI/UX, cleanest code)

- Best Use of Cloud & DevOps: (e.g., best infrastructure, CI/CD, scalability)

- Best Use of Data & Analytics: (e.g., most insightful data model, best visualizations)

- Best Use of ML & AI: (e.g., most creative or effective use of a model)

How are we going to judge all those projects and for what amount of time?(it should not take more than 1 week ).

PHASE 4 & 5

### Stage 4: The Recruiter Stage

Objective: To give participants direct access to tech recruiters and demystify the hiring process, teaching them the exact criteria used to select candidates.

#### Program Overview

- Duration: 2 Days (Recommended: Two consecutive evenings, or one full Saturday)

- Format: A 2-part series combining expert talks with practical, hands-on workshops.

- Resources: 1-2 tech recruiters (Ideally from "big tech" or prominent tech companies in Kenya).

#### Preparation: Action Items for Your Team

- Sourcing: Identify and reach out to recruiters from target companies (e.g., Google, Microsoft, Safaricom, Oracle, Cellulant, local scale-ups).

- Alignment Meeting: Hold a prep call with the confirmed recruiter(s). Share the program's 3-phase structure (Soft Skills, Hard Skills, Hackathon) so they can tailor their advice.

- Provide Topics: Give them the suggested 2-day topics below to build their presentations.

#### Proposed 2-Day Workflow

This structure separates the "getting noticed" from the "getting hired."

Day 1: "Passing the Filter: Your Application & Digital Brand"

- Objective: To teach participants how to build an application that gets past automated filters (ATS) and impresses a human recruiter in 6 seconds.

- Part 1: Recruiter Talk (60-90 Mins)

  - Topic: "The Anatomy of a 'Yes' Pile Resume."

  - Key Concepts to Cover:

    - Beating the Bot: How Applicant Tracking Systems (ATS) work and why keyword matching from the job description is critical.

    - The 6-Second Review: What recruiters actually look for first (Name, Last Role, Last Company, Dates, Keywords).

    - Impact vs. Responsibility: How to write bullet points using the "I achieved [X] by doing [Y], which resulted in [Z]" formula.

    - Showcasing Projects: How to list their Phase 3 hackathon project to demonstrate all 4 tech stacks (SE, Cloud, Data, ML).

    - The "Digital Handshake": The power of a professional LinkedIn profile and a clean, well-documented GitHub.

- Part 2: Practical Workshop (90 Mins)

  - Topic: "Live Resume & LinkedIn Teardown."

  - Format: Participants bring their current resumes/LinkedIn profiles. The recruiter(s) "live-critique" 3-5 volunteer submissions, applying the principles from the talk. This is highly engaging and provides immense practical value.

Day 2: "Closing the Deal: Mastering the Interview"

- Objective: To equip participants with the skills and confidence to excel in both behavioral and technical interviews.

- Part 1: Recruiter Talk (60-90 Mins)

  - Topic: "Beyond the Right Answer: What We Listen For in an Interview."

  - Key Concepts to Cover:

    - The Behavioral Interview: Explaining the STAR Method (Situation, Task, Action, Result) as the only way to answer behavioral questions ("Tell me about a time...").

    - The Technical Interview: It's not just about the right answer. It's about how they think. Recruiters listen for:

      - Asking clarifying questions.

      - Communicating their thought process (talking aloud).

      - Handling being stuck (staying calm, trying new approaches).

    - The "Culture Fit" Myth: It's really about "Coachability" and "Collaboration." How do they talk about their Phase 3 teammates?

    - Asking Smart Questions: Why "I have no questions" is the worst answer. Provide examples of great questions to ask a recruiter.

- Part 2: Practical Workshop (90 Mins)

  - Topic: "The Recruiter Q&A & Mock Interview."

  - Format: A 45-minute open Q&A. Followed by a 45-minute session where the recruiter(s) conduct 2-3 live 10-minute mock behavioral interviews with volunteers, providing public feedback.

### Stage 5: The Founder Stage

Objective: To focus on the "most important things" of entrepreneurship: idea validation and finding a path to market, using the hackathon project as a case study.

#### Program Overview

To address your concern about time, this stage is designed as a 2-Day "Founder Sprint" (e.g., two 3-hour evening sessions or one 6-hour Saturday) rather than two full days.

- Duration: 2 Days (Sprint Format)

- Format: Highly focused, practical workshops. This is less about theory and more about doing.

- Resources: 1-2 Founders (ideally from the Kenyan tech ecosystem who have successfully built a product from scratch).

#### Preparation: Action Items for Your Team

- Sourcing: Find 1-2 founders who are respected in the local tech community. A founder who has gone through an accelerator (e.g., YC, Antler) would be ideal.

- Alignment Meeting: Prep the founders. Explain that the goal is not to teach complex finance or legal structures, but to focus on the first two essential steps: Is the idea good? And how do you find users?

#### Proposed 2-Day Sprint Workflow

Day 1: "From Project to Product: Is This Idea Any Good?"

- Objective: To teach participants how to (ruthlessly) validate their hackathon idea and move from a "solution" to a "Minimum Viable Product (MVP)."

- Workshop 1: Customer Discovery (90 Mins)

  - Focus: "Stop Building, Start Listening."

  - Content: The founder explains that the biggest startup killer is building something nobody wants.

  - Key Concepts:

    - Problem-Solution Fit: Is the problem you think you're solving the real problem?

    - How to Talk to Users: The art of not asking, "Do you like my idea?" but instead asking open-ended questions about their current problems.

  - Task: Teams spend 45 minutes drafting 5 "customer discovery" questions and "interviewing" other teams.

- Workshop 2: Defining Your MVP (90 Mins)

  - Focus: "What is the 1% You Need?"

  - Content: The founder explains the concept of a Minimum Viable Product.

  - Task: Teams take their Phase 3 hackathon project (which is probably feature-heavy) and are forced to strip it down to the one single feature that provides the most value, and plan how to build only that.

Day 2: "From Product to Pitch: How Do You Find Users & Money?"

- Objective: To provide a simple, practical framework for finding initial users and explaining the business value of their project.

- Workshop 1: Go-to-Market (90 Mins)

  - Focus: "Your First 10 Users."

  - Content: A founder shares the non-scalable, "scrappy" things they did to get their first users (e.g., manual onboarding, personal emails, posting on specific forums).

  - Task: Teams brainstorm and present a 3-step plan to get their first 10 "non-friend/family" users for their MVP.

- Workshop 2: The 3-Minute Business Pitch (90 Mins)

  - Focus: "Pitching for Money vs. Pitching for Prizes."

  - Content: The founder explains how an investor pitch differs from a hackathon pitch. It focuses on:

    - Market Size (How big is this problem?)

    - Business Model (How will you make money?)

    - The Team (Why are you the ones to build this?)

  - Task: Teams rework their hackathon pitch into a 3-minute "investor-ready" pitch, which they practice in front of the group.

LIVE EVENT

- In this live event we are going to announce the event and broadcast it so others from different countries can also join in the same. We will need to discuss on whether it can be paid for or free,also considering it that it being free will need us to cater for all the expenses involved which will be too much.For now is not of much importance.

## THE NEXT STEPS/ROLES INVOLVED FOR THE SAME

- The information about the event is of real importance to reach to as many people as much as possible.That means we need to arrange posters and ways in which to do social media marketing in a way that will attract as many people as possible inclusive of videos.The posters must not only provide information but also lead someone to joining us.It must also show clarity in price to make people know beforehand what is expected of them.It should also focus on what they become at the end of it.

- We need to partner with other tech organizations like shecode to also help soo much with the outreach work.

- We also need to collect data from the expected participants and know what they would like the proffesionals to speak about.In terms of collecting data we also need to know how many will be joining us so we will circulate forms all through for people to register for the session,we will place a deadline for registering for the event but we will still bring in people who come after.

- We need to look for mentors/skilled proffesionals  and speak to them before hand,this means looking for mentors and having meetings with them in preparation for that event so they can prepare what to say.

- We will also need to have a whatsapp community featuring all these tech stacks 3 weeks before the event.

- We also need to determine what amount of finance we will need and to cover what specifically.

- We also need to start reaching out to recruiters as early as possible.

- We will need someone who will handle the numbers of people who register in terms of for the event since if we are not forming the community now,we will be sending follow up messages to whatsapp and email as well.

- We need someone to create the certificates for the participants.

- We will need someone to work on the prizes for the hackathon.

- We will also need moderators who will be in each session together with the speakers for moderation.

- We will also need judges for the hackathon to ensure that the projects meet the judging criterias.

- We will need someone to determine the tools needed for the projects and during the hackathon.

- We will need someone to handle the logistics for the live event which I really prefer if it can be done on any other day apart from Saturday.

### The 5 Core Leadership Roles

Here are the five key roles required to execute your program, with all tasks from your notes integrated into their responsibilities.

#### 1. Program Director (Head of Content & Curriculum)

This person is the "architect" of the entire participant journey. They own the "what" and "why" of the program, ensuring all 5 stages connect into one seamless, high-value experience.

- Curriculum Design:

  - Finalize and oversee the 3-week, 5-module curriculum for Phase 1 (Soft Skills).

  - Define the "4 major real-world problems" that will form the core of the Phase 2 (Hard Skills) panels and workshops.

  - Set the official theme (e.g., "Industry Sector") for the Phase 3 (Hackathon).

- Content Alignment:

  - Develop the detailed agendas, workshop formats, and key learning objectives for the Recruiter Stage and the Founder Stage.

- Quality Control:

  - Develop the official Hackathon Judging Criteria (e.s., scalability, problem-solution fit) that will be given to the judges.

  - Determine the tools and technologies (e.g., specific platforms, code repositories) that will be required for the hackathon projects.

  - Ensure all speaker and mentor content (from Phases 1-5) is high-quality and aligned with the program's objectives.

#### 2. Head of Marketing & Communications

This person is the "voice" of the program. They are responsible for user acquisition, public-facing brand, and ensuring the value proposition is clear, attractive, and reaches the widest possible audience.

- Brand & Strategy:

  - Develop the overall marketing strategy to "reach as many people as possible."

  - Craft the core message, focusing on the end-of-program transformation ("what they become").

- Campaign Execution:

  - Design and create all marketing materials, including compelling posters and social media videos.

  - Ensure all materials are persuasive, have a clear call-to-action (CTA) to "lead someone to joining," and clearly state the program price.

  - Execute the multi-channel social media marketing campaign.

- Communication:

  - Write the content for all follow-up messages (WhatsApp and Email) that will be sent to registered participants.

We do a marketing campaign and we are going to partner with different communities so that we reach to as many people as possible,the value we provide is that we will help them to enable their communities build beyond and know exactly what they ought to do.Generate slides that will make it clear of what we do.

#### 3. Head of Talent & Partnerships

This person is the "network" of the program. They are responsible for acquiring all the high-profile external people (mentors, partners, speakers) who will deliver the program's content.

- Talent Acquisition:

  - Identify, contact, and secure all 2-5 Phase 1 (Soft Skills) Mentors.

  - Identify, contact, and secure all 10+ Phase 2 (Hard Skills) Professionals.

  - Identify, contact, and secure the 1-2 "big tech" Recruiters for Stage 4.

  - Identify, contact, and secure the 1-2 Founders for Stage 5.

  - Identify, contact, and secure the Hackathon Judges.

- Relationship Management:

  - Schedule and conduct prep meetings with all speakers (mentors, professionals, recruiters) "beforehand" to align on content and "prepare what to say."

- Strategic Partnerships:

  - Forge strategic partnerships with other tech organizations (e.g., SheCode) to "help so much with the outreach work."

#### 4. Operations & Community Manager***********

This person is the "producer" of the program. They own the day-to-day participant experience, manage the community, and ensure all live events run flawlessly.

- Community Management:

  - Create and manage the WhatsApp community, ensuring the 4 tech stack channels are set up 3 weeks before the event.

- Event Logistics:

  - Plan, schedule, and execute the Pre-Program Info Session to educate participants and facilitate team formation.

  - Handle all logistics for the "live event," including finding a venue or platform and scheduling it on a non-Saturday (as preferred).

  - Recruit, train, and assign moderators for every live session.

- Participant Experience:

  - Act as the main point of contact for all participant questions and technical issues throughout the program.

  - Ensure all virtual rooms, recordings, and resources are available to participants.

#### 5. Finance & Administration Lead

This person is the "engine" of the program. They own the budget, data, registration process, and all administrative tasks that make the program possible.

- Finance:

  - Determine the total finance needed for the entire program.

  - Create a detailed budget specifying what all funds will cover (e.g., mentor stipends, prizes, platform fees).

- Registration & Data:

  - Create and circulate the registration forms to track participant numbers.

  - Create and circulate the form to collect data from participants on what they want Phase 2 professionals to speak about.

  - Manage the registration list, deadline, and the process for late joiners.

  - Handle all follow-up communication (WhatsApp/Email) to registrants to ensure they stay engaged.

- Administration:

  - Source, budget for, and procure all prizes for the hackathon.

  - Design, create, and distribute the official certificates to participants upon completion.

### Role 1: Head of Talent & Partnerships (The "Expert" Recruiter)

This person is responsible for securing all guest speakers: Mentors (Phase 1), Professionals (Phase 2), Recruiters (Stage 4), Founders (Stage 5), and Judges (Phase 3).

#### How Exactly to Do It:

- Create Your "Ask Packet": You are not just asking for a favor; you are offering a high-value opportunity. Create a professional 1-page PDF (or a 3-slide deck) that explains the program and answers "What's In It For Me?" (WIFM).

  - WIFM for Experts: "Get first-access, front-row scouting of Kenya's top, pre-vetted tech talent (SE, Cloud, Data, ML) after we've trained them in soft skills."

  - WIFM for Recruiters: "We are your pre-filter. We'll hand you a pool of candidates who have proven they can collaborate, build a real project, and communicate professionally."

- Build Your "Dream List": Use LinkedIn. Find 50+ tech leaders, founders, recruiters, and senior developers in Kenya who fit your target tracks. Look for people who are already posting about the "skills gap."

- Send the Outreach (The Template): Use a professional, direct, and respectful template via LinkedIn or Email.

  - Subject: Invitation to Shape Kenya's Next Tech Leaders: Skillyme x Secret Startups

  - Body: "Dear [Name], I've been following your work in [Their Industry], and your insights on [a specific topic they talk about] are exactly why I'm reaching out.


 We (Skillyme & Secret Startups) are running a 5-phase Tech Accelerator in January to solve the skills gap you've talked about—training students in soft skills, real-world tech challenges, and then having them build a full project.


 We are inviting you to be our expert guest for [Name the specific phase, e.g., "Phase 2: The Technical Deep-Dive"].


 The commitment is a single 60-minute virtual panel to share your insights on [Topic, e.g., "the major challenges in Cloud & DevOps"].


 This is a unique opportunity to scout 100+ of Kenya's top, pre-vetted tech talents. We handle all logistics; you just show up and share your wisdom.


 Would you be open to a 15-minute call next week to discuss this?


 Best, [Your Name]"

#### Goals for THIS MONTH (November):

- ✅ Finalize the 1-Page "Ask Packet" for experts.

- ✅ Build your "Dream List" of 50+ potential mentors, founders, and recruiters.

- ✅ Secure Your "Anchor Experts": Get a "YES" from at least 2-3 "big names" (well-known founders or recruiters). You will use their names in your marketing.

- ✅ Confirm at least 50% of all required speakers (e.g., 2/5 mentors for Phase 1, 5/10 mentors for Phase 2).

#### Goals for NEXT MONTH (December):

- ✅ Secure 100% of all mentors, professionals, recruiters, and hackathon judges.

- ✅ Hold the "Alignment Meetings" (as your PDF states) with all confirmed speakers to "prepare what to say" and send them the official briefing packets.

### Role 2: Head of Marketing & Communications (The "Community" Recruiter)

This person is responsible for getting participants (the students) and partners (the other tech communities).

#### How Exactly to Do It (Community Partner Outreach):

- Create Your "Partnership Deck": Create the 5-6 slide presentation I drafted for you. This is your tool to recruit other communities.

- Build Your Partner List: Identify all relevant tech communities (e.g., SheCode, DSCs at universities, local hubs).

- Pitch the "Win-Win": Your message to them is: "We are not competing; we are adding value. We have a fully-designed, expert-led program. We want to offer it to your members for free/low-cost to help them get job-ready. In return, we ask you to co-brand with us and share it with your community."

#### How Exactly to Do It (Participant Outreach):

- Finalize Marketing Assets: As your PDF states, create the posters and videos. Crucially, these must feature the names and faces of the "Anchor Experts" you secured in November. This is your biggest hook.

- Highlight the Transformation: Your messaging must be clear: "Before: A student with a GitHub. After: A job-ready professional with a portfolio project built with a 4-stack team, a certificate, and a network of CEOs and recruiters."

- Launch the Campaign: Use social media, your new community partners, and your (and Secret Startups') existing email/WhatsApp lists to drive people to the registration form.

#### Goals for THIS MONTH (November):

- ✅ Finalize the "Partnership Deck."

- ✅ Secure 10-15 "Community Partners" to help with outreach.

- ✅ Create the registration form (to collect data) and the "pre-event feedback form" (to ask what they want to learn).

- ✅ Finalize all poster/video assets, including the price and the "anchor expert" names.

#### Goals for NEXT MONTH (December):

- ✅ LAUNCH the marketing campaign across all channels.

- ✅ Get 80% of your target sign-ups by the end of the month.

- ✅ Send the "Phase 2 feedback form" to all registrants and give the data to the Program Director so they can finalize the mentor-talking points.

### Role 3: Operations & Community Manager

This person builds the "stadium" for the event to happen in.

#### How Exactly to Do It:

- Tech Stack: Finalize and pay for the tools. You need a paid Zoom/Meet account to handle large numbers and long-running breakout rooms.

- Recruit Moderators: You cannot run 5-6 sessions (General Assembly + 4 tracks) alone. Find reliable volunteers or team members now and train them on how to manage a room, assist a speaker, and keep time.

- Community Setup: Create the main WhatsApp Community and the 4 private "Track" channels (SE, Cloud, Data, ML).

#### Goals for THIS MONTH (November):

- ✅ Finalize and test all tech platforms (Zoom, Slido, etc.).

- ✅ Recruit and get "YES" from at least 4-5 session moderators.

#### Goals for NEXT MONTH (December):

- ✅ Launch the WhatsApp Community ("3 weeks before the event" as your PDF states).

- ✅ Run the "Pre-Program Info Session" (this is a critical event).

- ✅ Facilitate Team Formation: This is your #1 goal for this month. You must ensure 90%+ of participants are in a cross-functional team before Phase 1 begins in January.

### Role 4: Program Director (Head of Content)

This person turns the PDF outline into the actual content.

#### How Exactly to Do It:

- Write the "Task" Content: For Phase 1 (Soft Skills), you need to write the "Day 2-3 Group-Based Tasks" for all 5 modules.

- Finalize Hackathon Brief: Decide on the theme (e.g., "FinTech") and write the official "Problem Brief" and "Judging Criteria."

- Create "Speaker Packets": Create a 1-page briefing document for every single speaker (Mentors, Recruiters, Founders) that tells them the topic, the audience, and the key takeaways.

#### Goals for THIS MONTH (November):

- ✅ Finalize all 5 "Group Tasks" for Phase 1.

- ✅ Finalize the Hackathon Theme and the official "Judging Criteria" PDF.

#### Goals for NEXT MONTH (December):

- ✅ Create all "Speaker Packets" and send them to the Head of Talent (who will send them to the speakers during the alignment meetings).

- ✅ Use the student feedback data (from Marketing) to finalize the "4 major problems" for the Phase 2 mentors.

### Role 5: Finance & Administration Lead

This person manages the money and the "paperwork."

#### How Exactly to Do It:

- Finalize Budget: Get real quotes (don't guess) for all costs: prizes, platform fees, live event venue, mentor stipends (if any).

- Set Up Payments: How will people pay? M-PESA Paybill? A link on the website? Set this up and test it.

- Create Templates: Design the "Certificate of Completion" template.

#### Goals for THIS MONTH (November):

- ✅ Finalize the complete program budget.

- ✅ Set up and test the payment collection system.

- ✅ Finalize the certificate template.

#### Goals for NEXT MONTH (December):

- ✅ Start collecting program fees as people register.

- Create the "Master Spreadsheet" of all paid participants, their contact info, and their chosen tech track.

- ✅ Source and procure (or secure funding for) all hackathon prizes.

THIS WEEK GOALS

### Role 1: Head of Talent & Partnerships (The "Expert" Recruiter)

- This week I am going to confirm the attendance of 2/5  mentors in phase 1,software engineering expert(atleast 1),1 machine learning engineer,2 founders who can also connect us to recruiters.

### Role 2: Head of Marketing & Communications (The "Community" Recruiter)

- Using your marketing strategy start with our communities by registering users for the event,since you are the two of you ,one to create a grand poster today of which I’ll share the title after we have discussed with Peter today,and then one to use the slides I had created to reach out to the community heads of different tech communities,so go through the slides of which I’ll share in whatsapp and your goal for this week is to bring in 8 community heads of which we’ll all have a meeting with them on Saturday night,we look forward to you on that,Peter I’d also request that you will work with Isirri and look at what needs to be done to reach to more people but also be developing some kind of posters and templates leading to a link  that community heads will be posting and enabling us know the number of people to expect,remember to be clear with the price from the beginning of the posters,like provide the problem first,then the solution we are offering,the value they get and the price for the same at the end,you can use AI to provide  templates for the same.

### Role 3: Operations & Community Manager(we will discuss this role in our next meting)

### Role 4: Program Director (Head of Content)

- We do request if you could provide us with the contents for exactly how the sessions will be running that is the timetable and the contents for each session.

### Role 5: Finance & Administration Lead

- Please partner with the program director and also think about what are some of the expenses we do have to cover for phase 1,phase 2 and phase 3.